## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2231-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-3C-Autobots
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a helper I want to see a list of needs so that I choose what to contribute to. | Given that I am on the u-fund site when I am not on the Needs page then I must see a means to navigate to the Needs page.
Given that I am not on the Needs page when I choose the Needs page then I am taken to the Needs page.
Given that I am on the Needs page when there are no needs in the cupboard I see a message indicating that that there are no needs available to contribute.
Given that I am on the Needs page when there are needs in the cupboard then I see each need and short description.
Given that I am on the Needs page when there are needs in the cupboard then I see a means to add each need to my funding basket.
As a user I want to be able to see the login page so that I can login | Given I am a user I can navigate to the login page to login |  | CM; 3/20/24; Passed testing
As a helper I want to be able to learn about the cause I am contributing to so that I feel better about my donation | Given I click on anything that links to this page I should be able to see the page |  | JW; 3/16/24; Passed Testing
As a helper I want to be able to see my cart so that I can look at an overview of the needs I have selected and click the checkout button or remove needs from the list or adjust quantities of the needs | Given I am on the cart page and I have needs in my cart I should be able to press a checkout button |  | JW; 3/19/24; Passed testing
Given I am on the cart page and I have needs in my cart I should be able to remove the needs from my cart
Given I am on the cart page and I have needs in my cart I should be able to adjust the quantity of the needs
Given I am on the cart page and I have needs in my cart I should be able to see the needs in my cart
As a helper I want to be able to see all of the needs in the cupboard so that I can choose needs to contribute | Given I am a helper when I go to the cupboard I should be able to see all needs cupboard |  | DN; 3/19/24; Passed Testing
Given I am a helper when I go to the cupboard page I should be able to search for needs in the cupboard
As an admin I want to be able to view, add, remove, and update needs in the cupboard | Given I am on the cupboard logged in as an admin when I click the add button I can add a new need to the cupboard |  | II; 3/19/24; Passed Testing
Given I am on the cupboard logged in as an admin when I click the update button next to a need I can update the need
Given I am on the cupboard logged in as an admin when I click the delete button next to a need I can delete the need
As a helper I would want to remove needs from my basket so that I don't have to purchase them. | Given I am a helper when I try to remove a need from my basket it is no longer in my basket |  | JW; 3/19/24; Passed Testing
As a helper I want to be able to add needs to my basket so that I can select the needs I want to contribute and checkout. | Given I am a helper when I select a need to add to my basket it adds to the basket |  | DN; 3/19/24; Passed Testing